Risk Record — Potential Impact

This section completes note 3 of the risk record for all 44 identified risks. For each risk it analyses the potential impact across finances, infrastructure, reputation and marketplace, states the likelihood and magnitude, and identifies the objective or key dependency at stake.

Scoring follows the method set out in our Risk Protocols. Likelihood (L) and magnitude (M) are each scored 1 to 5 and multiplied to give a rating out of 25. Impact is recorded against the FIRM area most affected, with cross-effects noted, because our largest exposures interact rather than occur in isolation. Key dependencies are drawn from our stated list: people, premises, information, technology and suppliers.

The ratings below are inherent — the risk before existing controls are taken into account. Residual ratings follow from the Existing Controls section of the record.

Scoring key

| Score | Band | Required response |
| --- | --- | --- |
| 15–25 | Extreme | Escalate to executive management; treatment plan before next review |
| 10–14 | High | Crisis leadership team approves treatment; reviewed weekly |
| 5–9 | Moderate | Managed by the risk owner; reviewed monthly |
| 1–4 | Low | Accepted and monitored; reviewed quarterly |

F — Financial

| Ref | Code | Risk | L | M | Score | Potential impact |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | F1-E-01 | New pandemic costs exceed available funds | 3 | 4 | 12 High | Financial: response spending outruns available funds, forcing cuts to planned controls. Flows to Infrastructure, since remote-work equipment and IT resilience are the largest planned items, and to Reputation if service investment is deferred. Threatens the objective of funding the controls that keep essential services running. Dependency: technology, suppliers. |
| R-002 | F1-S-01 | Tiva support unavailable or terms unclear | 3 | 4 | 12 High | Financial: the support assumed throughout the plan does not arrive, or arrives on terms we cannot accept. Cross-effects in all four areas, since Tiva is relied on for funds, specialist expertise and independent control review. Undermines the resourcing assumptions in both Risk Strategy and Risk Resources. Dependency: suppliers and third parties. |
| R-003 | F2-P-01 | Resources do not match risk priorities | 4 | 3 | 12 High | Financial: allocation continues by habit rather than by rated exposure, leaving our highest risks under-resourced. Cross-effects on Infrastructure and Reputation, the two areas already identified as under-resourced relative to exposure. Conflicts directly with the allocation approach set out in Risk Resources. Dependency: people. |
| R-004 | F2-E-01 | Selling volatile assets at a loss to pay claims | 3 | 4 | 12 High | Financial: assets are sold into a falling market to meet claims, realising losses and sacrificing long-term returns. Cross-effects on Marketplace through reduced investment income and on Reputation if liquidity pressure becomes visible. Threatens the objective of meeting policyholder obligations without weakening the balance sheet. Dependency: information. |
| R-005 | F3-T-01 | Cyber fraud causes false claim payouts | 3 | 4 | 12 High | Financial: fraudulent claims are paid because remote working has weakened verification and approval. Cross-effects on Reputation through regulatory exposure and on Infrastructure, since the gap is technological. Strikes internal controls, already one of our weakest areas. Dependency: technology, information. |
| R-006 | F3-S-01 | Important controls depend on outsourced vendors | 4 | 3 | 12 High | Financial: key controls sit with vendors whose own pandemic disruption we cannot see or manage. Cross-effects on Infrastructure and Reputation, since accountability for a vendor failure remains ours regardless of cause. Dependency: suppliers and third parties. |
| R-007 | F3-S-02 | Bank partners delay or fail to remit premiums | 2 | 4 | 8 Moderate | Financial: premium remittance is delayed or fails, interrupting cash inflow at a point when liquidity is already under pressure. Cross-effect on Marketplace if collection problems affect renewal. Threatens the objective of maintaining premium collection. Dependency: suppliers. |
| R-008 | F3-S-03 | Reinsurers cannot pay recoveries | 2 | 5 | 10 High | Financial: our main protection against an accumulation of claims fails. Unlikely in any given period but potentially severe, with cross-effects on Reputation and on our ability to meet policyholder obligations. Dependency: suppliers and third parties. |
| R-009 | F3-E-01 | Bond issuers default | 2 | 4 | 8 Moderate | Financial: defaults in a stressed credit market reduce asset values and investment income. Cross-effect on Marketplace. Dependency: information, through portfolio monitoring. |
| R-010 | F4-E-01 | Weather catastrophe exceeds reserves and cash | 2 | 5 | 10 High | Financial: an Ontario catastrophe produces claims beyond what reserves and cash can absorb. Low likelihood in any one period but severe, with cross-effects on Reputation and Marketplace if settlement is delayed. Reserve adequacy is already a known weakness. Dependency: suppliers, through repair capacity. |
| R-011 | F4-E-02 | Travel, medical and cancellation claims rise together | 4 | 4 | 16 Extreme | Financial: claims that normally spread across the year arrive at once, concentrating payout into a short window. Cross-effects on Infrastructure through claims-handling capacity and on Reputation through settlement delay. Directly threatens reserve adequacy. Dependency: people, information. |
| R-012 | F4-E-03 | Lower interest rates raise pension liabilities | 5 | 3 | 15 Extreme | Financial: with the policy rate at its lower bound, falling yields raise the present value of long-dated pension and life liabilities while reducing the income available to fund them. Near-certain in the current environment. Cross-effect on Marketplace. Dependency: information. |

I — Infrastructure

| Ref | Code | Risk | L | M | Score | Potential impact |
| --- | --- | --- | --- | --- | --- | --- |
| R-014 | I1-P-01 | No remote work plan exists | 5 | 4 | 20 Extreme | Infrastructure: every subsequent remote-working control has to be designed under crisis conditions rather than drawn from a plan. Cross-effects in all three other areas: unsecured access threatens Reputation, service interruption threatens Marketplace, improvised spending threatens Finance. This is the foundational gap from which several other risks follow. Dependency: people, technology. |
| R-015 | I1-P-02 | Staff availability falls through illness and isolation | 4 | 3 | 12 High | Infrastructure: a 50-person workforce has little redundancy, so absence removes capability rather than slowing it. Cross-effects on Reputation and Marketplace through service delay. Threatens the objective of maintaining claims processing and customer support. Dependency: people. |
| R-016 | I1-P-03 | Specialist roles are hard to replace quickly | 2 | 4 | 8 Moderate | Infrastructure: a single departure or illness in a specialist role removes a capability we cannot rebuild at short notice. Cross-effects on Reputation and Marketplace. Dependency: people. |
| R-017 | I1-P-04 | No employee owns risk management | 5 | 3 | 15 Extreme | Infrastructure: with no one holding risk management as a primary responsibility, risks are identified late or missed. Certain, since this describes our current structure. Cross-effects across all four areas, because it degrades our ability to see any of them. Dependency: people. |
| R-018 | I2-T-01 | Not enough equipment for remote work | 5 | 4 | 20 Extreme | Infrastructure: roughly 50 desktops and a handful of laptops cannot equip a remote workforce, and the shortfall bites immediately rather than gradually. Cross-effects on Marketplace through lost service capacity and on Reputation through delay. Dependency: technology, suppliers. |
| R-019 | I2-E-01 | Restrictions limit access to premises and servers | 4 | 3 | 12 High | Infrastructure: public health restrictions delay maintenance and hardware repair on on-site servers. Cross-effect on Marketplace if a failure cannot be attended promptly. Dependency: buildings, technology. |
| R-020 | I3-T-01 | Remote-access safeguards are insufficient | 4 | 5 | 20 Extreme | Infrastructure: inadequate VPN, authentication and training expose systems and customer data. Magnitude is maximum because data exposure is explicitly where our appetite is lowest. Cross-effects on Reputation through regulatory and trust damage and on Finance through penalties and remediation. Dependency: technology, information. |
| R-021 | I3-T-02 | Network and internet connection become a bottleneck | 4 | 3 | 12 High | Infrastructure: the internal network and single external connection cannot carry load that has shifted to remote access. Cross-effects on Marketplace and Reputation through degraded service. Dependency: technology, suppliers. |
| R-022 | I3-T-03 | Network outage halts core operations | 3 | 5 | 15 Extreme | Infrastructure: an outage stops claims processing, premium collection and customer support at the same time, which is all three stated objectives at once. Cross-effects are total rather than partial. IT resilience carries our highest individual risk score. Dependency: technology, suppliers. |
| R-023 | I3-P-01 | Six-person IT team cannot monitor at all hours | 4 | 3 | 12 High | Infrastructure: incidents occurring outside working hours are detected late, extending both outage and exposure. Cross-effect on Reputation if a breach runs undetected. Dependency: people, technology. |
| R-024 | I3-T-04 | Capacity and recovery arrangements are untested | 5 | 2 | 10 High | Infrastructure: we do not know whether our recovery arrangements work until we need them. Impact is realised through other risks rather than on its own, but it raises the magnitude of every incident that follows. Dependency: technology. |
| R-025 | I4-P-01 | Remote work slows service restoration | 4 | 3 | 12 High | Infrastructure: coordinating a fix across a dispersed team lengthens outages. Cross-effects on Reputation and Marketplace. Dependency: people, technology. |
| R-026 | I4-S-01 | Critical supplier reduces or ends a key service | 3 | 4 | 12 High | Infrastructure: hosting, backup, security advice, printing or mailing is withdrawn under the supplier’s own pandemic pressure. Cross-effects on Reputation, since secure destruction and policy mailing carry compliance obligations, and on Finance through replacement cost. Dependency: suppliers. |
| R-027 | I4-T-01 | No disaster recovery procedure suits remote work | 4 | 4 | 16 Extreme | Infrastructure: recovery procedures assume an office that nobody is in, so they cannot be executed as written. Cross-effects across all areas during any incident, since recovery is what limits every other impact. Dependency: people, technology, buildings. |

R — Reputation

| Ref | Code | Risk | L | M | Score | Potential impact |
| --- | --- | --- | --- | --- | --- | --- |
| R-028 | R1-P-01 | Claims and enquiries exceed capacity; responses late | 4 | 3 | 12 High | Reputation: travel claims, enquiries and coverage disputes outrun staff capacity and responses fall outside acceptable timeframes. Cross-effects on Marketplace through customer loss and Finance through complaint handling. Breaches the response-time thresholds set in Risk Appetite. Dependency: people. |
| R-029 | R1-C-01 | Customers under financial pressure treated insensitively | 3 | 3 | 9 Moderate | Reputation: customers in difficulty receive treatment that damages trust at the moment it matters most. Cross-effect on Marketplace through retention. Dependency: people. |
| R-030 | R2-C-01 | Unclear statements confuse customers about coverage | 3 | 4 | 12 High | Reputation: inconsistent or unclear communication leaves customers mistaken about what they are covered for. Cross-effects on Finance through disputes and on Reputation again through regulatory attention. Dependency: information. |
| R-031 | R2-P-01 | Remote work causes employee stress; support insufficient | 4 | 3 | 12 High | Reputation: a sudden shift to remote work isolates staff without adequate support. Cross-effects on Infrastructure through availability and on Marketplace through service quality. Conflicts with the stated objective of protecting employees. Dependency: people. |
| R-032 | R3-P-01 | Workload causes processing errors and incomplete records | 4 | 3 | 12 High | Reputation: increased volume produces errors and gaps in records. Cross-effects on Finance through rework and on compliance, since record-keeping is a regulatory obligation rather than an internal preference. Dependency: people, information. |
| R-033 | R3-T-01 | Remote work exposes customer data | 3 | 5 | 15 Extreme | Reputation: unauthorised access to customer information. Maximum magnitude, because this is explicitly where our appetite is lowest and the consequences land on regulation, finances and trust simultaneously. Dependency: technology, information. |
| R-034 | R3-C-01 | FSRA, FINTRAC and OSFI requirements not fully identified | 2 | 4 | 8 Moderate | Reputation: obligations are missed because they were never catalogued, and the gap surfaces at examination rather than before. Cross-effect on Finance through penalties. Dependency: information, people. |
| R-035 | R4-P-01 | Staff shortages delay customer-facing operations | 4 | 3 | 12 High | Reputation: visible service delay in the operations customers actually experience. Cross-effects on Marketplace and Finance. Dependency: people. |
| R-036 | R4-C-01 | Service timelines and coverage limits unclear | 3 | 3 | 9 Moderate | Reputation: avoidable complaints arise from expectations we never set clearly. Cross-effect on Marketplace. Dependency: information. |

M — Marketplace

| Ref | Code | Risk | L | M | Score | Potential impact |
| --- | --- | --- | --- | --- | --- | --- |
| R-037 | M1-E-01 | Individual customers reduce, defer or cancel coverage | 4 | 3 | 12 High | Marketplace: household income pressure drives lapse, deferral and downgrading across personal lines. Cross-effects on Finance through premium income and on Reputation if cancellation handling is poor. Dependency: information, including early warning from brokers. |
| R-038 | M1-E-02 | Small business clients reduce, defer or cancel coverage | 3 | 3 | 9 Moderate | Marketplace: business closures and revenue loss reduce commercial exposure and premium. Cross-effect on Finance. Note: scope depends on whether we write commercial lines, which the team should confirm. Dependency: information. |
| R-039 | M1-E-03 | Travel demand collapses; drivers seek lower auto premiums | 5 | 4 | 20 Extreme | Marketplace: travel insurance sales stop while drivers who have ceased commuting press for rebates. Near-certain and already underway. Cross-effects on Finance through revenue and on Reputation if rebate expectations are not met. Dependency: information. |
| R-040 | M2-E-01 | Competitors attract customers with cheaper rates | 3 | 3 | 9 Moderate | Marketplace: price-sensitive customers move in a market where switching costs are low. Cross-effect on Finance. Dependency: information. |
| R-041 | M3-E-01 | Volatility and low rates cut asset values and income | 5 | 4 | 20 Extreme | Marketplace: asset values and investment income fall at the same time, which is near-certain in current conditions. Cross-effects run through Finance across reserves, liquidity and the ability to fund operations. Dependency: information. |
| R-042 | M3-E-02 | Global economic pressure weakens Tiva | 3 | 4 | 12 High | Marketplace: our parent group is weakened by the same conditions affecting us, reducing the support assumed throughout the plan. Cross-effects in all areas, since Tiva underpins funds, expertise and assurance. Dependency: suppliers and third parties. |
| R-043 | M3-E-03 | Government support does not reach customers adequately | 3 | 3 | 9 Moderate | Marketplace: affordability pressure persists longer than forecast because relief does not land where expected. Cross-effect on Finance through lapse and arrears. Dependency: external conditions. |
| R-044 | M4-S-01 | Shortage of repair services, parts and materials | 4 | 3 | 12 High | Marketplace: settlement is delayed and claim severity rises on policies already priced and bound, which cannot be repriced mid-term. Cross-effects on Finance through severity and Reputation through delay. Dependency: suppliers. |
| R-045 | M5-T-01 | Cannot keep up with surge in online demand | 4 | 3 | 12 High | Marketplace: demand shifts online faster than our systems and staff can absorb. Cross-effects on Infrastructure through capacity and Reputation through visible service failure. Dependency: technology, people. |

Summary of the inherent risk profile

Of 44 risks assessed, 11 rate Extreme, 24 High and 9 Moderate. The Extreme ratings cluster in Infrastructure, which is consistent with the Riskiness Index finding that IT resilience carries our highest individual risk score. Four of them — no remote-work plan (R-014), insufficient equipment (R-018), inadequate remote-access safeguards (R-020) and no disaster recovery procedure for remote work (R-027) — are preconditions rather than events: they raise the magnitude of most other risks in the register and should be treated first.

The Marketplace Extremes (R-039, R-041) and the interest rate exposure (R-012) are near-certain rather than possible, and are scored on that basis. They are largely outside our control, which means the response is financial resilience rather than prevention.